## NIST Rating Guide
Rating | Likelihood | Impact
Very Low | Very unlikely / minimal chance | Minimal adverse effect
Low | Unlikely | Limited adverse effect
Moderate | Possible | Serious adverse effect
High | Likely | Severe adverse effect
Very High | Highly likely / near certain | Multiple severe or catastrophic adverse effects
Reference | NIST SP 800-30 Rev. 1 — Guide for Conducting Risk Assessments

## Risk Register
Risk ID | Asset | Threat Event | Vulnerability / Predisposing Condition | Likelihood | Impact | Risk Level | Rationale
R-01 | Customer Database | Unauthorized Access to Customer Data | Weak Access Controls | High | Very High | Very High | Weak access controls may expose sensitive customer data.
R-02 | E-Commerce Website | Web Application Attack | Unpatched Software Components | Very High | Very High | Very High | Unpatched components may enable exploitation and system compromise.
R-03 | Corporate Email | Phishing Attack | Lack of Security Awareness Training | Very High | Very High | Very High | Untrained employees may be more susceptible to phishing attempts.
R-04 | Employee Laptops | Malware Infection | Outdated Endpoint Protection | Moderate | Very High | High | Outdated endpoint protection may fail to detect current malware.
R-05 | Cloud Storage | Unauthorized Data Exposure | Misconfigured Access Permissions | Very High | Very High | Very High | Misconfigured permissions may expose stored business data.
R-06 | Internal Network | Unauthorized Network Access | Weak Network Segmentation | Moderate | High | High | Weak segmentation may allow unauthorized lateral access.
R-07 | Admin Accounts | Privileged Account Compromise | Multi-Factor Authentication Not Enforced | Moderate | Very High | High | Compromised privileged credentials may provide extensive system access.
R-08 | Payment Information | Payment Data Theft | Inadequate Protection of Sensitive Payment Data | Low | High | High | Insufficient protection may expose sensitive payment information.
R-09 | Corporate Email | Business Email Compromise | Weak Email Authentication Controls | High | Very High | Very High | Weak email authentication may enable spoofing or account misuse.
R-10 | E-Commerce Website | Denial-of-Service Attack | Insufficient Availability and Resilience Controls | Low | High | Moderate | Insufficient resilience may lead to service disruption during an attack.
R-11 | Employee Laptops | Unauthorized Data Access After Device Loss | Full-Disk Encryption Not Enforced | High | High | High | An unencrypted lost device may expose locally stored business data.
R-12 | Cloud Storage | Permanent Data Loss | Inadequate Backup and Recovery Controls | High | High | High | Weak backup and recovery controls may prevent restoration after data loss.

## Risk Treatment Plan
Risk ID | Treatment | Treatment Action | Owner | Priority | Target | Residual Risk
R-01 | Mitigate | Enforce least privilege and conduct periodic access reviews. | IT / Security | High | 30 days | Moderate
R-02 | Mitigate | Establish patch management and promptly remediate vulnerable components. | IT / Development | High | 30 days | Moderate
R-03 | Mitigate | Implement recurring phishing and cybersecurity awareness training. | HR / Security | High | 30 days | Moderate
R-04 | Mitigate | Deploy and maintain updated endpoint protection across employee devices. | IT / Security | High | 30 days | Moderate
R-05 | Mitigate | Correct cloud permissions and perform periodic access reviews. | Cloud / Security | High | 14 days | Moderate
R-06 | Mitigate | Segment critical systems and restrict unnecessary network access. | Network / Security | High | 60 days | Moderate
R-07 | Mitigate | Enforce MFA and strengthen privileged account controls. | IT / Security | High | 14 days | Moderate
R-08 | Mitigate | Encrypt sensitive payment data and restrict access to authorized personnel. | IT / Security | High | 30 days | Moderate
R-09 | Mitigate | Strengthen email authentication, filtering, and anti-phishing controls. | IT / Security | Medium | 30 days | Low
R-10 | Mitigate | Implement DDoS protection and availability/resilience measures. | Network / Security | Medium | 60 days | Low
R-11 | Mitigate | Enforce full-disk encryption on employee laptops. | IT / Security | High | 30 days | Low
R-12 | Mitigate | Establish regular backups and test restoration procedures. | IT / Security | High | 30 days | Low

## Control Assesment
Risk ID | Relevant NCNICC Control | Current Status | Gap Identified | Recommended Action
R-01 | 1-2-2 Identity & Access Management | Partially Implemented | Weak access controls | Enforce least privilege and periodically review access rights.
R-02 | 1-3-2 Systems & Information Processing Devices Protection | Partially Implemented | Unpatched software components | Establish patch management and promptly apply security updates.
R-03 | 1-5-2 Cybersecurity Awareness & Training | Not Implemented | No security awareness training | Provide recurring phishing and cybersecurity awareness training.
R-04 | 1-3-2 Systems & Information Processing Devices Protection | Partially Implemented | Outdated endpoint protection | Deploy and maintain current endpoint malware protection.
R-05 | 1-7-2 Data & Information Protection | Partially Implemented | Misconfigured cloud permissions | Apply least-privilege permissions and review cloud access regularly.
R-06 | 1-5-2 Network Security Management | Partially Implemented | Weak network segmentation | Segment critical systems and restrict unnecessary network access.
R-07 | 1-2-2 Identity & Access Management | Partially Implemented | MFA not enforced for admin access | Enforce MFA and strengthen privileged access management.
R-08 | 1-8-2 Cryptography | Partially Implemented | Sensitive payment data inadequately protected | Encrypt sensitive payment data in transit and at rest.
R-09 | 1-4-2 Email Protection | Partially Implemented | Weak email authentication/protection | Strengthen email filtering and authentication controls.
R-10 | 1-5-2 Network Security Management | Partially Implemented | Insufficient availability/resilience controls | Implement network resilience and DDoS protection measures.
R-11 | 1-7-2 Data & Information Protection | Not Implemented | Full-disk encryption not enforced | Enforce encryption on employee laptops and protect encryption keys.
R-12 | 1-9-2 Backup Management | Partially Implemented | Inadequate backup and recovery controls | Perform regular backups and periodically test restoration.
Framework | NCA NCNICC 1:2025
Assessment note | Statuses are simulated for the fictional NovaCart environment and are based on the gaps defined in the risk register.